## Sheet1
Start date: | 2025-01-01
End date: | 2025-04-01
Project duration: | 3 months
Task | Task Description | Priority | Skills
1 | Create a login page that receives 2 inputs which are Username and Password | High | HTML , CSS
2 | Add submit button for the login page and redirect it to the homepage. | High | HTML, Javascript
3 | Add javascript to validate the username and password. Prompt error message for invalid input. | High | Javascript
4 | Add "Show Password" checkbox below the password input. Default value of the checkbox is unchecked. | Medium | HTML, Javascript
5 | Change the background color of the login page to blue and add image logo at the top of the screen. | Low | CSS, HTML
6 | Add a logout button at the top right of the screen for homepage. | Medium | HTML , CSS, Javascript
7 | Create a prompt message to confirm for logout. | Low | Javascript