## WBS_Zam
Project Name |  |  |  | Created By
Filename | Details_WBS.xlsx |  |  | Created Date |  | 2025-01-14
Remarks |  |  |  | Updated By
|  |  |  | Updated Date |  |  |  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8
Project Start Date | 01/14/2025 |  | Overall Progress
 | time axis 2023-11-06 to 2023-12-31
Item No. | Task Description | Assigned To | Progress | Plan Start | Plan End | Actual Start | Actual End | Remarks
1 | WBS001_UI | Nuramira Binti Ahmad Mahmud | To do | 01/14/2025 | 01/28/2025
2 | WBS002_UI | Nuramira Binti Ahmad Mahmud | To do | 01/29/2025 | 02/12/2025
3 | WBS003_UI | Nur Ain Binti Mahamad Salleh | To do | 01/14/2025 | 01/28/2025
4 | WBS004_UI | Nur Ain Binti Mahamad Salleh | To do | 01/29/2025 | 02/05/2025
5 | WBS001PRO001_CreateLoginFunction | Jannatil Anwar Bin Jaharuddin | To do | 01/14/2025 | 01/28/2025
6 | WBS001PRO002_CreateLogoutFunction | Nur Ain Binti Mahamad Salleh | To do | 02/06/2025 | 02/12/2025
7 | WBS001PRO003_CreateRegisterFunction | Muhammad Izzun Mustaqim Bin Ismahdi | To do | 01/14/2025 | 01/28/2025
8 | WBS001PRO004_CreatePasswordResetFunction | Jannatil Anwar Bin Jaharuddin | To do | 01/29/2025 | 02/12/2025

## Setting (hidden)
TBL_Member | Plan Start Date | 1
Member | Plan End Date | 2
Zamzarina | Plan Same Date | 0
Dayalan
Aziana
Arief | J9
All
GI68